## Cover
| Prime Contractors Name: |  |  |  | Insert Name Here
Contents:
|  | 1 | Vendor Staffing
|  | 2 | Utilities Staffing
Instructions
The Vendor will be responsible for identifying the necessary resources to successfully
install the proposed solution in the identified timeframe.
Eastern Municipal Water District
Staffing Matrix
Attachment D

## Vendor Staffing Matrix
Instructions: Vendor will provide named roles for the Prime Vendor or Subcontractor. Identify % allocation per month. This table should include both onsite and offsite resources and allocation for Vendor. Phases should be modified to match Vendor's project plan. Overall project plan and staffing MUST be provided. A Second chart is provided below in which Vendor must fill out the number of weeks onsite by month for each resource proposed.
Vendor Staffing Allocation
|  |  | Planning |  | Analysis |  |  |  | Design & Construction |  |  |  | Testing & Training | [13 empty] | Post Implementaion Support
Go-Live
Month Number |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Project Month |  | 2019-03-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01
Business Days In Month |  |  | 21 | 21 | 23 | 19 | 23 | 20 | 20 | 23 | 19 | 21 | 22 | 22 | 20 | 22 | 22 | 20 | 23 | 19 | 21 | 21 | 21 | 21 | 21 | 22 | 20 | 22 | 22 | 19
Total Available Hours in Month |  |  | 168 | 168 | 184 | 152 | 184 | 160 | 160 | 184 | 152 | 168 | 176 | 176 | 160 | 176 | 176 | 160 | 184 | 152 | 168 | 168 | 168 | 168 | 168 | 176 | 160 | 176 | 176 | 152
Role | Responsible Party | 2019-03-01: Avg % Allocation; 2019-03-01: *** Enter % Allocaiton Per Month ***
Example: Project Manager | Prime Vendor | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
Total Resource Days |  |  | 21 | 21 | 23 | 19 | 23 | 20 | 20 | 23 | 19 | 21 | 22 | 22 | 20 | 22 | 22 | 20 | 23 | 19 | 21 | 21 | 21 | 21 | 21 | 22 | 20 | 22 | 22 | 19
Total Resource Hours |  |  | 168 | 168 | 184 | 152 | 184 | 160 | 160 | 184 | 152 | 168 | 176 | 176 | 160 | 176 | 176 | 160 | 184 | 152 | 168 | 168 | 168 | 168 | 168 | 176 | 160 | 176 | 176 | 152
FTE Count | bar: 2019-03-01 to 2021-06-01
Instructions: For each role outlined in the above table please indicate the number of ONSITE weeks expected per month. | bar: 2019-03-01 to 2019-08-01
Vendor On-Site Weeks
|  |  | Planning |  | Analysis |  |  |  | Design & Construction |  |  |  | Testing & Training | [13 empty] | Post Implementaion Support
Go-Live
Month Number |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Project Month |  | 2019-03-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01
Business Days In Month |  |  | 21 | 21 | 23 | 19 | 23 | 20 | 20 | 23 | 19 | 21 | 22 | 22 | 20 | 22 | 22 | 20 | 23 | 19 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
Total Available Hours in Month |  |  | 168 | 168 | 184 | 152 | 184 | 160 | 160 | 184 | 152 | 168 | 176 | 176 | 160 | 176 | 176 | 160 | 184 | 152 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168
Role | Responsible Party | 2019-03-01: Avg % Allocation; 2019-03-01: *** Enter # of Weeks Onsite Per Month ***
Example: Project Manager | Prime Vendor |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Total Weeks On-Site |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
# Resources Onsite | bar: 2019-03-01 to 2021-06-01
Average Onsite Resources | 1

## EMWD Staffing
Instructions: Vendor will provide named roles EMWD will be responsible for filling to support 100% knowledge transfer for the new CIS, CSS and Mobile System. EMWD has provided descriptions and percent allocation to the project in Section 7 of the RFP that they feel will be necessary. Vendor should modify this to align with their project plan and experience.
Staffing Plan
|  | Planning |  | Analysis |  |  |  | Design & Construction |  |  |  | Testing & Training | [12 empty] | Post Implementaion Support
Go-Live
Month Number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Project Month | 2018-11-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01
Business Days In Month |  | 21 | 21 | 23 | 19 | 23 | 20 | 20 | 23 | 19 | 21 | 22 | 22 | 20 | 22 | 22 | 20 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
Total Available Hours in Month |  | 168 | 168 | 184 | 152 | 184 | 160 | 160 | 184 | 152 | 168 | 176 | 176 | 160 | 176 | 176 | 160 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184 | 184
Role | 2018-11-01: Average % Allocation; 2018-11-01: ***Input Expected % Allocaiton***
PMO
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
WORKSTREAMS FUNCTIONAL/Testers/Trainers
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
TESTING TEAM
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
ORGANIZATION CHANGE
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
INFRASTRUCTURE
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
TECHNICAL TEAM
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
Total Resource Days |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Resource Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTE Count |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0